## Slide 1: Performance Management Strategic Initiative January 2017 Update
Gurleen Roberts

## Slide 2: Strategic Initiative Overview
Project 1: InsightVision (PM system)
Project 2: Quality Improvement

## Slide 3: Project 1: InsightVision (PM system)
Project | SMART Goals | Actions | FY17 Qrtrs |  |  |  | Status | Progress Notes
 |  |  | 1 | 2 | 3 | 4 |  | 
InsightVision | Prepare InsightVision system for full implementation July 1, 2017 | 1. By January 2017, integrate operational metrics into IV |  |  |  |  |  | All are in there. Not all programs have updated. List is pending.
 |  | 2. From September 2016 to December 2016, Program Managers will have “Coaching Sessions” with an IV consultant and Gurleen/Katie to upgrade scorecards. Plan to have all program scorecards drafted by 12/31/16 |  |  |  |  |  | Pushed to Jan 31, 2017.
 |  | 3. From January 1-31, 2017, Center Directors will have an opportunity to review drafted program scorecards. |  |  |  |  |  | Pushed to Feb 1-28, 2017
 |  | 4. From February 1-28, 2017, Dr. Kennedy will have an opportunity to review drafted program scorecards. |  |  |  |  |  | Pushed to Mar-Apr 2017. PMs will “show-and-tell” their scorecards to Dr. K ,GR, Center Director during Mar-Apr center mtgs.
 |  | 5. Hope to have all program scorecards approved and ready for Retreat on March 27-8, 2017 |  |  |  |  |  | Pushed to June 30, 2017. Missing program scorecards: Chronic Disease, HIV, Pharmacy, Vital Records
 |  | 6. Focus on creating operational scorecards for Admin functions (IT, HR, Accounting/Budget/Finance), Communications, and OQM by June 30, 2017. |  |  |  |  |  | Done with operational dashboards in IV. Will get these owners trained after program scorecards are completed.
Notes: Next FY, focus on community scorecards since CHIP metric discussion will begin September 2017.

## Slide 4: Project 1: InsightVision (PM system)
Project | SMART Goals | Actions | FY17 Qrtrs |  |  |  | Status | Progress Notes
 |  |  | 1 | 2 | 3 | 4 |  | 
InsightVision | 2. By September 30, 2016, update Program Summary Tools, focusing on the balanced scorecard, logic model, and strategy map. | 1. Emily will help input submitted PSTs into IV by 12/31/16. |  |  |  |  |  | Done
 |  | 2. Inputting past PST BSC data into IV |  |  |  |  |  | Done
 |  | 3. By 6/30/17, program strategy maps will be updated with new objectives after scorecards are drafted. |  |  |  |  |  | Pending

## Slide 5
Project | SMART Goals | Actions | FY17 Qrtrs |  |  |  | Status | Progress Notes
 |  |  | 1 | 2 | 3 | 4 |  | 
InsightVision | 3. By June 30, 2017, results of the Turning Point assessment will be used to identify projects for improving the performance management system. | 1. Take Turning Point Assessment in January, during LT meeting. Review results at during March LT retreat. |  |  |  |  |  | Pushed to March. Culture of Quality Assessment will be in February.
 |  | 2. Use results to ID gaps for improvement projects by June 30, 2017 |  |  |  |  |  | 
Project 1: InsightVision (PM system)

## Slide 6: Project 2: QI
Project | SMART Goals | Actions | FY17 Qrtrs |  |  |  | Status | Progress Notes
 |  |  | 1 | 2 | 3 | 4 |  | 
Quality Improvement | 1. By September 30, 2016, Business QA/QI and Clinical QI teams adopt charter and start working on QI projects. | 1. Business QA/QI has begun a QI project on updating billing notes. |  |  |  |  |  | Team currently not meeting due to staff turnover in IT and Billing departments.
 |  | 2. Clinical QI will have their first meeting October 13, 2016 |  |  |  |  |  | 
 | 2. By June 30, 2017/8/9, update QI plan | 1. Align QI plan with best-practice QI plans and accurately reflect CDPH’s QI activities during annual revision. |  |  |  |  |  | 
 |  | 2. Research and create better support for programmatic QI teams, such as a QI toolbox. |  |  |  |  |  | Working on this continuously. QI 301 will focus more on QI tools and facilitation
 |  | 3. Results of NACCHO’s QI Assessment will be used to evaluate agency’s progress towards a culture of quality every year, and use results to update QI plan priorities and projects. |  |  |  |  |  | Will do this with LT and Quality Council in February 2017.

## Slide 7: Project 2: QI
Project | SMART Goals | Actions | FY17 Qrtrs |  |  |  | Status | Progress Notes
 |  |  | 1 | 2 | 3 | 4 |  | 
Quality Improvement | 3. By June 30, 2017, create QI IQ series training plan to reflect requirements for staff tier and update in QI plan. | 1. Implement mandatory QI 101 Training monthly through June 30, 2017 or until all staff are trained. Afterwards, roll out quarterly. |  |  |  |  |  | Almost all current staff are trained. Remaining are new staff hired within previous 6 months.
 |  | 2. By September 30, 2016, roll out QI 201: LEAN & Process Mapping training, and then present bi-annually. |  |  |  |  |  | Presenting to supervisors in February, and remaining in June. Scheduled a third in November.
 |  | 3. By December 31, 2016, roll out QI 301: Facilitation training and then present bi-annually. |  |  |  |  |  | Pushed to March. Partially developed already.
 |  | 4. By March 30, 2017, roll out QI 401: QI & Performance Management training and then present bi-annually. |  |  |  |  |  | This may change since InsightVision has recorded custom BSC webinars for us.

## Slide 8
Performance Management Strategic Initiative Team Charter

## Slide 9: Performance Management Strategic Initiative Team Charter (cont’d)