Appendix A

Oneida County Health Department

Rapid Cycle Improvement Quick Strike Project Form

| Project Title: | Increasing QuickStrike Project Submission |
| --- | --- |
| Submitted By: | QI Team |
| Briefly identify or describe the program, project or process that should be addressed with an RCI project: | OCHD staff submission of RCI quickstrike projects are decreasing as the year progresses. The goal of this project is to increase submission and creating awareness of quickstrike submission through a promotion event. AIM: By September 30, 2015, increase quickstrike submissions by at least 100% (from 6 in Q1 and Q2 to at least 12 by 9/30/15). |
| Priority: | High Medium Low |
| Anticipated Outcome(s)? | Increased quickstrike submissions. |
| Who should be on this RCI team? Who should be the lead? | QI Team |
| Baseline Data to Support Change? | Submissions: 2- Jan; 1- Feb; 2- March; 1- April 5 in Quarter 1, 1 in Quarter 2 |
| What was the FINANCIAL IMPACT of this change project? (e.g. Increased revenue? Reduced costs? Increased staff retention?) | Improving staff efficiency |

| AIM Statement | By September 30, 2015, 10 quickstrike projects will be submitted. |
| --- | --- |
| Step # | Start Date | End Date | Change Made What changes were made? | Outcome What were the results? How do they compare with baseline measure? | Next Steps What is your next step? Adopt, adapt, or abandon the change made? |
| 1 | 7/20/15 | 7/20/15 | QI Project Proposal created (replaced index card submission) | Simplified card | Adapt- include admin items on back of card |
| 2 | 8/1/2015 | 8/30/2015 | Develop Promo” Have no Fear, QI is Here” to incentivize staff to submit QI projects. | Staff submitted 15 projects over the course of the promotion. | Adopt- have regular event to promote submissions- maybe annually? |
| 1 | 9/21/15 | 9/21/15 | QI Project Proposal updated to include admin use items on back of card | Revised card and replaced for staff use | Adapt- add date |
| 1 | 10/5/15 | 10/5/15 | QI Project Proposal updated to include projected start date for submitting staff | Added date to help clarify when project would be started | Adopt |
| FINAL OUTCOME: Please briefly describe final outcome of RCI project (new form developed, updated P & P, etc) | By September 30, 2015, 21 quickstrike projects have been submitted. Consider regular “promotion” of submissions- perhaps through monthly staff meeting shout outs, etc. Increased quickstrike submission by 250%. |

| Project put into QI Project Summary Document? | Yes Not Yet |
| --- | --- |

Additional Notes: