## Target References
Target References
1 | Safety/Ergonomics
2 | People Travel
3 | Product Travel
4 | Space
5 | Lead Time
6 | Cycle Time
7 | Set-up time
8 | Quality
9 | Productivity
10 | Volume
11 | Inventory
12 | Crew Sized

## Team 1
Kaizen Newspaper
Action Items/Issues
Team: Paul and Linda Area: Scheduling and Pre-work
Item | Target Ref** | Problem to be solved | Action needed | Resp. | Start Date | Est. completion date | Actual completion date | Progress Results (Quantify) | Status Updates
1 | 7 | Surveyors need self-addressed envelopes | Distribute self-addressed envelopes to surveyors | Shannon Walker | 2012-07-01 | 2012-07-15 | 2012-08-03 |  | 8/3: completed
2 | 9 | Entry of the assignments & creation of the templates for survey into ACO/ ILRS are not timely | Incorporate in office protocols | Shannon Walker | 2012-07-01 | 2012-09-30 | 2012-09-30 |  | 09/30/2012 This is now completed after the surveyors conference call. 8/3: OP will address specific timelines 7/16:Dependent on getting the new scheduling spreadsheet
3 | 7 | Scheduling surveys requires multiple databases and emails | Create a single master scheduling spreadsheet | Shannon Walker | 2012-07-01 | 2012-07-30 | 2012-07-27 |  | 7/27: completed as a result of the July 30 conference call
4 | 9 | No single location for all survey related scheduling information | Recommend creating a calendar in Outlook that can be uploaded with pending surveys, anticipated leave (loaded by team members) etc. | Shannon Walker | 2012-07-01 | 2012-09-30 |  |  | 8/3: Rachael will confirm staff access to this outlook 7/16:A special clinical facilities outlook calendar has been created
5 | 6 | There is a lot of rework when scheduling surveys | Incorporate regular conference calls with team to discuss schedules | Linda Foss | 2012-07-01 | 2012-08-31 | 2012-07-30 | Will be last Monday of each month | 7/30: completed as a result of the conference call7/16:first will be July 30th
6 | 7 | Send spreadsheet of next surveys due to team before conference call | Incorporate in new office protocol | Shannon Walker | 2012-07-01 | 2012-08-31 | 2012-07-30 | Will send monthly schedule one month in advance for conference call (Sept schedule issued by end of July) | 7/30: completed 7/16: SW will ensure it's sent before July 30th
7 |  | All leave slips to be submitted month in advance | Incorporate in new office protocol | Linda | 2012-07-01 | 2012-07-15 | 2012-07-30 |  | 7/30: completed 7/16:monthly conference call will address this expectation
8 | 9 | Need a complete checklist for surveyors as to what is needed to complete a survey | Create checklist | Shannon Walker | 2012-07-01 | 2012-08-31 | 2012-08-31 | Reference Liz’s checklist | 8/3: OP will address 7/16: rachel will start with Liz's version
9 | 9 | After conference call, give final schedule to admin to create survey templates and ILRS assignments | Office protocol w/ templates | Shannon Walker | 2012-07-01 | 2012-08-31 | 2012-08-31 | Agreement with Fire Marshal – once we send schedule we can cancel but not add anything new. | 8/3: OP will address 7/16: SW will incorp into draft OP.
10 | 9 | ILRS action step not always complete and accurate | Create action items worksheet for ILRS survey steps | Shannon Walker | 2012-07-01 | 2012-08-31 | 2012-09-30 |  | 08/31: will train at 09/20/2012 meeting for use in checklist 8/3: OP will address 7/16: SW will incorp into draft OP.
11 | 7 | Need to create “pending survey” files (survey prep) | Incorporate in new office protocol | Shannon Walker | 2012-07-01 | 2012-08-31 |  | Need single “clearing house” physical file started at beginning of survey process (vs. putting in “facility” file). Will need change in process as to what goes in facility file | 10/31/2012 testing process8/3: OP will address 7/16: not much done yet.
|  | Can we get an exception to the 60 mile travel restriction? | Work with Director | Trent Kelly/Shannon | 2012-07-01 | 2012-08-10 | 2012-08-31 |  | 8/10: discussed with Magby; he's willing to consider exceptions on case by case basis if requested well in advance of survey.
12 | 2 | Can we get an exception to the 40 hr. work week under federal labor law | Work with Chief Administrator to identify exceptions | Trent Kelly/Shannon | 2012-07-01 | 2012-08-10 | 2012-08-31 | Trent talk to Sam about possible “exemption” to 40 hr work week (fed rule). If you don’t reach 60 mile mark, must come home that day so inadequate on-site time. | 8/9: SW and TK met with Sam; seeking "OT exempt" status thru Fed gov for any additional IIO staff not advisable. 8/3: TK & SW will schedule time with SM to discuss PH3 haviing independent discretion to reach OT exemmpt classifiication 7/16: trent in discussions with folks
13 | 9 | Timesheet is limited to reporting only 8 hrs. a day. | Work with HR to address Timesheet issues | Shannon | 2012-07-01 | 2012-08-31 | 2012-08-31 |  | 8/3: SW to investigate further 7/16: trent/SW in discussions.
14 | 9 | Not a good system in place for distributing to team/admin CMS updates to forms etc | Incorporate in new office protocol | Rachael Lindstedt | 2012-07-01 | 2012-08-31 | 2012-08-31 |  | 10/30 still CMS ASPEN database issue 8/3: Work in Progress 7/16: new aspen version may fix; rachel will look into this.

## Team 2
Kaizen Newspaper
Action Items/Issues
Team: Rachael, Cherie, Shannon, Trent, Paul, Larry Area: Post-exit
Item | Target Ref** | Problem to be solved | Action needed | Resp. | Start Date | Est. completion date | Actual completion date | Notes | Status Updates
1 | 9 | Need to attach pdf of SOD in ILRS | Incorporate in new office protocol | Shannon Walker | 2012-07-01 | 2012-07-15 |  |  | 8/3: OP in works. 7/16: SW sez it can be done; we see that it's incorp into draft protocal
2 | 9 | Admin are not notified of changes in team | Incorporate into new office protocol | Linda Foss | 2012-07-01 | 2012-07-15 | 2012-09-20 |  | 8/3: OP in works. 7/16: after exit interview team leader's "final" email will provide team members; date start and exit, etc. SW will ensure this checklist made part of protocal.
3 | 9 | 3 emails about survey results from team lead to admin reduced to 1 only | Eliminated emails from process | Linda Foss | 2012-07-01 | 2012-07-15 | 2012-09-20 |  | 8/3: OP will direct team lead to load exit date into ILRS. Only email will be when POC is approved. 7/16: see above
4 | 3 | We should email notification to hospital that Fire Marshal report is complete | Incorporate in new office protocol | Linda Foss | 2012-07-01 | 2012-08-01 | 2012-08-01 | Required by law – all correspondence from us | 8/1: completed. 7/16: LF needs to address with Karen Jones
5 | 9 | Need to clarify what if any dates team members can enter into ILRS/ASPEN | Incorporate in office protocol | Linda Foss | 2012-07-01 | 2012-08-15 | 2012-09-20 |  | 8/3: OP will address action items. 7/16: part of action item work flow chart that will be incorp in OP.
6 | 3, 5 | Instead of waiting for physical packet Can info scanned/emailed to admin | Incorporate in office protocol | Linda/Shannon | 2012-07-01 | 2012-09-30 |  | 09/20/2012 at this time they are mailing their packets to us.Do all surveyors have scanner? | 8/3: Will address at Lean II in September 7/16: all members have scanners; will be part of OP.
7 | 3 | Team leader alone approves POC | Incorporate in office protocol | Linda Foss | 2012-07-01 | 2012-07-31 | 2012-07-31 |  | 7/31: Completed 7/16: put in OP.
8 | 8 | Inconsistent expectations for submitting survey notes and packets | Create standardized process for submitting surveyor packets to admin | Linda Foss | 2012-07-01 | 2012-08-31 | 2012-09-20 | 09/20/2012 Survey Checklist is being tested. Relates to overall office protocol | 8/3: Work in Progress 7/16: part of checklist for OP.
9 | 8 | Surveyor should clearly indicate notes portion (same as #4 | Create standardized process for submitting surveyor packets to admin | Shannon Walker | 2012-07-01 | 2012-08-15 | 2012-09-20 | 09/20/2012 Survey Checklist is being tested. Relates to overall office protocol | 8/3: Work in Progress 7/16: part of checklist for OP (may be both state audit and/or cms expectation)
10 | 8 | Need to have 1539 accuracy e.g. comments missing due to aspen (ask Rachel | Incorporate into office protocol | Linda Foss | 2012-07-01 | 2012-08-31 | 2012-09-20 | CMS Database issue - working on solution | 8/3: OP to address. 7/16: CMS req.; rachel will contact Bartley for tech solution.
11 | 9 | Archive survey notes and other related docs together | Create standardized process for submitting surveyor packets to admin | Shannon Walker | 2012-07-01 | 2012-10-01 |  | 10/30/2012 Still working on retention schedule for survey notes. Check on state audit to see if we must keep survey notes and archive and for how long? | 8/3: Confirmed audit requires retention of survey notes. State and Federal retention schedules to be finalized. 7/16: SW will run this down.
12 | 8 | Information for State survey file and fed goes missing from High Density files (Certificate of need, construction review, etc) | Incorporate into office protocol (sign/in/out sheet and electronic means of tracking | Shannon | 2012-07-01 | 2012-08-31 | 2012-08-31 | Generally we should be working towards getting files archived sooner since once they’re gone we don’t have to be responsible for them | 8/3: Robin is testing and finalizing protocol. 7/16: Robin Sheldon working on "sign out" sheet & "task sheet" thru outlook for files.
13 | 6 | In state only survey, is a progress report required and if it is then does it need to be approved (by team or lead?) | Team already verified, not required; Create Attestation | Linda Foss | 2012-07-01 | 2012-08-15 | 2012-07-02 | Linda to consult SOM etc. | 7/2: LF directive to staff. no progress report needed in state or fed survey
14 | 5 | Even if progress report needed why must we send hardcopy | Once approved, team lead can send electronic version to be copied and filed by admin | Shannon | 2012-07-01 | 2012-08-15 | 2012-07-02 | Hard copy required, no change needed | see above
15 | 6 | If Medicare, is progress report needed for non-condition level surveys? | Eliminate progress report and have hospital submit attestation | Linda Foss | 2012-07-01 | 2012-08-15 | 2012-07-02 | Even if progress report required can it be replaced with an attestation | see above
16 | 6 | 670 hours often missing for progress reports in ACO | Incorporate into office protocol | Shannon & Linda | 2012-07-01 | 2012-07-15 | 2012-07-02 | 670 hours are time spent by surveyors to ensure compliance | see above
17 | 6 | Scanned survey packet should be attach in ILRS | Incorporate in new office protocol | Shannon Walker | 2012-07-01 | 2012-08-15 |  |  | (see #1 entry)
18 | 6 | Can we close survey in ILRS before progress report approved | Incorporate in new office protocol | Linda Foss | 2012-07-01 | 2012-08-31 | 2012-07-02 | Attestation? | see above
19 | 3 | Send electronic courtesty copy Statement Of Deficiencies to hospital | Incorporate in new office protocol | Linda Foss | 2012-07-01 | 2012-08-31 |  | This electronic version would be “courtesy copy” only and hardcopy would be the official in terms of setting timeframes | 8/3:Work in Progress 7/16: must be done by team lead; need training of new OP.
20 | 9 | ILRS action step not always complete and accurate | Create action items worksheet for ILRS survey steps | Shannon Walker | 2012-07-01 | 2012-08-31 | 2012-08-31 | Must make sure that action items make sense and verify action items used in reports. Follow up with appropriate training. | 09/10/2012 will train staff in ILRS Action Items 8/3: OP will address. 7/16: action item checklist being worked up.
21 | 3 | Hospitals would like electronic approval of POC | Incorporate in new office protocol | Linda Foss | 2012-07-01 | 2012-08-31 |  | As long as we file hardcopy and do this as “courtesy” | 8/3: OP will address. 7/16: should be team leaders responsibilty; need training of new OP.