Prenatal care coordination (PNCC)

quality improvement storyboard

| Local Health Department Name: | Clark County Health Department |
| --- | --- |
| Address: | 517 Court Street RM 105 Neillsville, WI 54456 |
| Phone Number: | 715-743-5105 |
| Size: | 6 Full Time Employees-1 Part Time Employee |
| Population served: | 34,412 residents-diverse population-Caucasian, Hispanic, African American (primarily Caucasian) estimated 1/3 of total county population is comprised of Amish/Mennonites |
| Project Title: | Improving the Quality and Efficiency of the Prenatal Care Coordination Program (PNCC) |

PLAN

Identify an opportunity and

Plan for Improvement

- Getting Started

Problem: The provision of Prenatal Care Coordination (PNCC) services has been occurring in Clark County for many years. However, the health department recognized the program has not been evaluated or updated since 2007.  The policy and procedure was outdated and did not adhere to the requirements in the WI Medicaid PNCC Services Handbook, program forms were outdated, no flowsheet/checklist was in place to ensure consistency and chart compliance, and staff was not properly oriented to the program.  Additionally, no clear billing guidelines were in place.

2.  Assemble the Team

The health department committed the time of the Lead Public Health Nurse as the project coordinator, as well as staff Public Health Nurses and the Health Officer to assist with the project.

- Brittany Mews, RN BSN-Lead PHN

- Cortney Olejniczak-RN BSN-PHN

- Sabrina Meddaugh-RN BSN-PHN

- Susan Backaus-RN BSN-PHN

- Robert Leischow-MPH-Health Officer

3.  Examine the Current Approach

After a chart review process, the department found 0% of the PNCC charts were in compliance and reflective of the WI Medicaid PNCC Services Handbook.  We also tracked our PNCC Medicaid reimbursement from 2007 through 2011 and discovered we were being reimbursed only about 30% of the maximum allowable reimbursement per client.

Aim Statement: By November 30, 2012, after the Clark County Health Department’s PNCC policy and procedure has been updated reflecting the WI Medicaid PNCC Services Handbook, program forms have been updated, a PNCC flowsheet/checklist developed, and staff training conducted on the PNCC revisions, 100% of the PNCC client charts will be in compliance after a chart review process.

Sub Aim Statement:   Billing guidelines will be established. This will result in an increase in Medicaid reimbursement for the PNCC program from an average of $270.00 per client in 2011 to an average of $540.00 or more per client in 2012, a 200% projected increase in revenue. (Total maximum Medicaid reimbursement is $887.46 per client).

4.  Identify Potential Solutions

- Update the PNCC policy and procedure

- Update all program forms

- Develop a chart audit flowsheet/checklist

- Train staff on the new revisions

- Establish billing guidelines

5.  Develop an Improvement Theory

By updating the PNCC policy and procedure and program forms,  developing  a chart audit flowsheet/checklist, training staff, and establishing billing guidelines, it will result in 100 % of charts being in compliance and a 200% increase in Medicaid revenue.

DO

Test the Theory for Improvement

6.  Test the Theory

The project coordinator reviewed the WI Medicaid PNCC Handbook protocols, updated the PNCC policy and procedure to reflect the Medicaid guidelines, updated all program forms, developed a chart audit flowsheet/checklist as well as a billing guideline cheat sheet, and trained staff on the new revisions.

A trial process began on 08/15/12. Staff followed the newly developed policy and procedure and utilized the new forms, including the billing cheat sheet.  Average Medicaid reimbursement was tracked per client.

STUDY

Use Data to Study Results

of the Test

7.  Study the Results

In October 2012, two PNCC chart audits were conducted.  Both of these charts were 100% in compliance, utilizing the newly developed chart audit flowsheet/checklist.  The preliminary results of 100% chart compliance compared to the baseline data of 0% chart compliance indicates the test has been successful.

In October 2012, 4 client’s Medicaid reimbursement totals were analyzed.  These 4 clients were a part of the new program revisions, and the nurses utilized the new billing guidelines established.  The average reimbursement the department received between these four clients was $671.61 per client, a 250% increase (+$406.91) from the 2011 average reimbursement of $270.00. In addition to the Medicaid increase, it was discovered the Medicaid denials also decreased.  This data signifies the billing guideline cheat sheet helped increase the revenue and streamlined the billing process.

ACT

Standardize the Improvement and Establish Future Plans

8.  Standardize the Improvement

On November 01, 2012, the health department adopted and standardized the process.  The new PNCC policy and procedure and program forms, including billing guideline cheat sheet, were formally approved by the health department’s director.

9.  Establish Future Plans

Additional PNCC chart audits will be performed on a quarterly basis to ensure compliance.  The department plans on sustaining the momentum of the project by reviewing and updating the program policy and procedure at least on an annual basis, continue to update program forms as needed, and continue to track Medicaid reimbursement revenue.

# Text boxes

http://www.co.clark.wi.us/

517 Court St., Room 105 * Neillsville, WI 54456-1972 * (715)743-5105 * Toll Free 1-877-743-5105 * Fax (715)743-5115

Clark County Health Department