| QI Team Charter |
| --- |
| 1. Team Name: | 2. Version: | 3. Subject (Target Area): |
| The Point at Tobias QI Grant Team | THREE | Teen Clinic Utilization |
| 4. Problem/Opportunity Statement: |
| Targeting the teen population for family planning services requires novel approaches. We can have a significant impact on the teen pregnancy rate within the county with a marketing process that is more effective. |
| 5. Team Sponsor (Health Official): | 6. Team Leader: |
| Nick Davidson/Matt Petrofes | Michelle McKinzie |
| 7. Team Members: | Role: |
| Suzan Alexander | Teen Clinic Site Coordinator |
| Beth McArthur | Marketing Expert |
| Pam McNeil | Lead Admin Supervisor |
| Regina Stevens | Outreach Coordinator |
| Cathy Voelker | SCHD Site Manager |
| Jamie Whiteside | Admin Supervisor |
| 8. Process Improvement Area: |
| Teen-Specific Marketing Strategies |
| 9. Initial AIM Statement: |
| By November 30, 2012, increase the average utilization rate of 13-19 year olds at the teen center from 60% to 80%. |
| 10.Revised AIM Statement(s): |
| By November 30, 2012, we will increase the average number of units (1 unit = 15 minutes) appointed per day at the teen center by 13-19 year olds from 44 to 58 (or, 80% of our current capacity). |
| 11. Scope (Boundaries)/Team Authority: |
| Must use marketing techniques approved by SC DHEC Central Office |
| 12. Customers (Internal and External): | 13. Customer Needs Addressed: |
| Teens in Spartanburg County | Low Cost Family Planning Services |
| 14. Success Measures (What does success look like?): |
| Within 60 days of implementing marketing strategy #1, 2, and 3, the average number of units per day will increase by 11% percent. (May 1st) |
| Within 60 days of implementing marketing strategy #4, the average number of units per day will increase by 10% percent. (Sept. 1st) |
| Within 60 days of implementing marketing strategy #5 and 6, the average number of units per day will increase by 11% percent. (Nov. 1st) |
| 15. Considerations (Assumptions/Constraints/Obstacles): |
| May have limited ability to implement certain marketing tactics (such as using social media outlets, radio ads, etc.) |
| 16. PDSA Timeline: | Date: |
| Plan | April 1st – June 30th |
| Do | July 1st – September 30th |
| Study | October 15th – October 30th |
| Act | November 1st – November 30th |
| 17. Meeting Frequency: Bi-weekly during Plan phase than at least monthly thereafter. |
| 18. Communication Plan (Who, How and When): Team meetings, emails, meeting minutes |
| 19. Stakeholders (Internal and External): |
| Clients, staff, community |
| 20. Improvement Theories (If…Then): |
| If we implement targeted marketing strategies | Then we will improve utilization of the teen center. |
| If | Then |