## GANNT Report_11.30.12
Data Base Compliance Project: Status Report as of 11/30/2012
KEY:
Data Base Name | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | Comments | C - Complete
Birth Registry (Paper Worksheet) | IP | IP | IP | IP | IP | IP | C | Changes made. Hospital worksheets are being piloted in 5 locations. Parent worksheets have been QA'd and will be translated into Spanish for use effective March 2013. | IP - In Progress
CT Immunization Registry and Tracking System (CIRTS) (Electronic Database) | IP | IP | IP | NC |  |  |  | Changes identified; Revised Planning form for paper worksheet changes sent to database owner on 8/28; 9/4 update: Program manager stated changes could not be made due to higher priorities, lack of funding, and lack of resources (including staff) | NC - Not Complete
Health Practitioner Licensure (eLicense) (Paper Worksheet) | IP | IP | IP | IP | IP | IP | IP (95% done) | Revised Planning form for paper worksheet changes sent to database owner on 8/13
Adult Blood Lead Epidemiology and Surveillance (ABLES) (Electronic Database) | IP | IP | IP | IP | IP | IP | C | Changes identified; sent planning form 10/2; Changes to the Maven system too costly to implement, but as of 11/5 changes were made to the DPH "customizable" page and an open text gender, other please specify field was added.
CT Influenza Surveillance: Now part of CT EDSS (Paper Worksheets) | IP | IP | IP | IP | IP | IP | IP | Change Request Sent to Steering Committee member; sent planning form 10/2; Stated that they can make the changes to the paper worksheets effective 1/1/13
CT Influenza Surveillance: Now part of CT EDSS (Electronic Database) | IP | IP | IP | IP | IP | IP | C | Sent planning form 10/2; Changes to the Maven system too costly to implement, but as of 11/5 changes were made to the DPH "customizable" page and an open text gender, other please specify field was added.
Tuberculosis Program (formerly TIMS) | NC | [6 empty] | Not able to make changes due to lack of time and staffing
Occupational Injury and Illness Surveillance (Paper Worksheet) | IP | IP | IP | IP | IP | IP | IP | Changes identified; sent planning form 10/2; data owner is looking into the feasibility to make the changes - meet with Dept. of Labor-the form owner.
Occupational Injury and Illness Surveillance (Electronic Database) | IP | IP | IP | IP | IP | IP | C | Changes identified; sent planning form 10/2; Changes to the Maven system too costly to implement, but as of 11/5 changes were made to the DPH "customizable" page and an open text gender, other please specify field was added.
Surveillance Epidemiology and End Results (SEER) Data Management System (Electronic Database) | IP | IP | IP | IP | IP | IP | IP | Changes identified; sent planning form 10/2; Stated will make changes to electronic database effective 12/12/12
GANTT CHART Data | Status Report as of 11/30/2012; Based on project ending November 30, 2012
| Database | Date Identified | Days Completed | Days Remaining | Date Terminated | Important Updates | Status Check | Comment
| Births (Paper) | 2012-05-10 | 202 | 0 | 2012-11-28 | 2012-11-30 |  | QA done 11/28
| CIRTS (EDB) | 2012-05-10 | 117 | 0 | 2012-09-04 | Status Reports
| HP Licensure (Paper) | 2012-05-10 | 204 | 0 |  | 2012-07-01 |  | Ongoing
| ABLES (EDB) | 2012-05-22 | 189 | 0 | 2012-11-27 | 2012-08-30 | 2012-11-30 | QA done 11/27
| CT EDSS (Paper) | 2012-05-22 | 192 | 0 |  | 2012-10-01 |  | Ongoing
| CT EDSS (EDB) | 2012-05-22 | 189 | 0 | 2012-11-27 | 2012-10-01 |  | QA done 11/27
| TB (TIMS) | 2012-05-22 | 1 | 0 | 2012-05-22 | 2012-11-30
| OIISS (Paper) | 2012-05-22 | 192 | 0 |  |  |  | Ongoing
| OIISS (EDB) | 2012-05-22 | 189 | 0 | 2012-11-27 |  |  | QA done 11/27
| SEER (EDB) | 2012-05-22 | 192 | 0 |  |  |  | Ongoing

## GANNT Report_10.31.12
Data Base Compliance Project: Status Report as of 11/5/2012
KEY:
Data Base Name | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | Comments | C - Complete
Birth Registry (Paper Worksheet) | IP | IP | IP | IP | IP | IP |  | Planning Form completed by 8/6, but needs to be modified | IP - In Progress
CT Immunization Registry and Tracking System (CIRTS) (Electronic Database) | IP | IP | IP | NC |  |  |  | Changes identified; Revised Planning form for paper worksheet changes sent to database owner on 8/28; 9/4 update: Program manager stated changes could not be made due to higher priorities, lack of funding, and lack of resources (including staff) | NC - Not Complete
Health Practitioner Licensure (eLicense) (Paper Worksheet) | IP | IP | IP | IP | IP | IP |  | Revised Planning form for paper worksheet changes sent to database owner on 8/13
Adult Blood Lead Epidemiology and Surveillance (ABLES) (Electronic Database) | IP | IP | IP | IP | IP | IP |  | Changes identified; sent planning form 10/2; Changes to the Maven system too costly to implement, but as of 11/5 changes can be made to the DPH "customizable" page and an open text gender, other please specify field can be added.
CT Influenza Surveillance: Now part of CT EDSS (Paper Worksheet) | IP | IP | IP | IP | IP | C |  | Change Request Sent to Steering Committee member; sent planning form 10/2; Stated that they can make the changes to the paper worksheets effective 1/1/12
CT Influenza Surveillance: Now part of CT EDSS (Electronic Database) | IP | IP | IP | IP | IP | NC |  | Change Request Sent to Steering Committee member; sent planning form 10/2; Changes to the Maven system too costly to implement
Tuberculosis Program (formerly TIMS) | NC | [6 empty] | Not able to make changes due to lack of time and staffing
Occupational Injury and Illness Surveillance (Paper Worksheet) | IP | IP | IP | IP | IP | IP |  | Changes identified; sent planning form 10/2; data owner is looking into the feasibility to make the changes.
Occupational Injury and Illness Surveillance (Electronic Database) | IP | IP | IP | IP | IP | IP |  | Changes identified; sent planning form 10/2; Changes to the Maven system too costly to implement, but as of 11/5 changes can be made to the DPH "customizable" page and an open text gender, other please specify field can be added.
Surveillance Epidemiology and End Results (SEER) Data Management System (Electronic Database) | IP | IP | IP | IP | IP | C |  | Changes identified; sent planning form 10/2; Stated can make changes to electronic database effective 12/1/12
GANTT CHART Data | Status Report as of 11/5/2012; Based on project ending November 30, 2012
| Database | Date Identified | Days Completed | Days Remaining | Date Terminated | Important Updates | Status Check
| Births | 2012-05-10 | 179 | 25 |  | 2012-11-30
| CIRTS | 2012-05-10 | 117 | 0 | 2012-09-04 | Status Reports
| HP Licensure | 2012-05-10 | 179 | 25 |  | 2012-07-01
| ABLES | 2012-05-22 | 167 | 25 |  | 2012-08-30 | 2012-11-05
| CT EDSS | 2012-05-22 | 157 | 0 | 2012-10-26 | 2012-10-01
| TB (TIMS) | 2012-05-22 | 1 | 0 | 2012-05-22 | 2012-11-30
| OIISS | 2012-05-22 | 167 | 25
| SEER | 2012-05-22 | 133 | 0 | 2012-10-02

## GANNT Report_9.30.12
Data Base Compliance Project
KEY:
Data Base Name | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | Comments | C - Complete
Birth Registry | IP | IP | IP | IP |  |  |  | Planning Form completed by 8/6, but needs to be modified | IP - In Progress
CT Immunization Registry and Tracking System (CIRTS) | IP | IP | IP | NC |  |  |  | Changes identified; Revised Planning form for paper worksheet changes sent to database owner on 8/28; 9/4 update: Program manager stated changes could not be made due to higher priorities, lack of funding, and lack of resources (including staff) | NC - Not Complete
Health Practitioner Licensure (eLicense) | IP | IP | IP | IP |  |  |  | Revised Planning form for paper worksheet changes sent to database owner on 8/13
Adult Blood Lead Epidemiology and Surveillance (ABLES) | IP | IP | IP | IP |  |  |  | Changes identified; sent planning form 10/2
CT Influenza Surveillance: Now part of CT EDSS | IP | IP | IP | IP |  |  |  | Change Request Sent to Steering Committee member; sent planning form 10/2
Tuberculosis Program (formerly TIMS) | NC | NC | NC | NC |  |  |  | Not able to make changes due to lack of time and staffing
Occupational Injury and Illness Surveillance | IP | IP | IP | IP |  |  |  | Changes identified; sent planning form 10/2
Surveillance Epidemiology and End Results (SEER) Data Management System | IP | IP | IP | IP |  |  |  | Changes identified; sent planning form 10/2
GANTT CHART Data | Status Report as of 10/2/2012; Based on project ending November 30, 2012
| Database | Date Identified | Days Completed | Days Remaining | Date Terminated | Important Updates | Status Check
| Births | 2012-05-10 | 145 | 59 |  | 2012-11-30
| CIRTS | 2012-05-10 | 117 | 0 | 2012-09-04 | Status Reports
| HP Licensure | 2012-05-10 | 145 | 59 |  | 2012-07-01
| ABLES | 2012-05-22 | 133 | 59 |  | 2012-08-30 | 2012-10-02
| CT EDSS | 2012-05-22 | 133 | 59 |  | 2012-10-01
| TB (TIMS) | 2012-05-22 | 1 | 0 | 2012-05-22 | 2012-11-30
| OISS | 2012-05-22 | 133 | 59
| SEER | 2012-05-22 | 133 | 59

## GANNT Report_8.30.12
Data Base Compliance Project
KEY:
Data Base Name | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | Comments | C - Complete
Birth Registry | IP | IP | IP |  |  |  |  | Planning Form completed by 8/6, but needs to be modified | IP - In Progress
CT Immunization Registry and Tracking System (CIRTS) | IP | IP | IP |  |  |  |  | Changes identified; Revised Planning form for paper worksheet changes sent to database owner on 8/28 | NC - Not Complete
Health Practitioner Licensure (eLicense) | IP | IP | IP |  |  |  |  | Revised Planning form for paper worksheet changes sent to database owner on 8/13
Adult Blood Lead Epidemiology and Surveillance (ABLES) | IP | IP | IP |  |  |  |  | Changes identified
CT Influenza Surveillance: Now part of CT EDSS | IP | IP | IP |  |  |  |  | Change Request Sent to Steering Committee member
Tuberculosis Program (formerly TIMS) | NC | NC | NC |  |  |  |  | Not able to make changes due to lack of time and staffing
Occupational Injury and Illness Surveillance | IP | IP | IP |  |  |  |  | Changes identified
Surveillance Epidemiology and End Results (SEER) Data Management System | IP | IP | IP |  |  |  |  | Changes identified
GANTT CHART Data | Status Report as of 8/30/2012
| Database | Date Identified | Days Completed | Days Remaining | Date Terminated | Based on project ending November 30, 2012
| Births | 2012-05-10 | 112 | 92 |  | 2012-11-30
| CIRTS | 2012-05-10 | 112 | 92 |  | Status Reports
| HP Licensure | 2012-05-10 | 112 | 92 |  | 2012-07-01
| ABLES | 2012-05-22 | 100 | 92 |  | 2012-08-30
| CT EDSS | 2012-05-22 | 100 | 92 |  | 2012-10-01
| TB (TIMS) | 2012-05-22 | 1 | 0 | 2012-05-22 | 2012-11-30
| OISS | 2012-05-22 | 100 | 92
| SEER | 2012-05-22 | 100 | 92

## GANTT Report_7.1.12
Data Base Compliance Project
KEY:
Data Base Name | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | Comments | C - Complete
Birth Registry | IP | IP | [5 empty] | Changes identified | IP - In Progress
CT Immunization Registry and Tracking System (CIRTS) | IP | IP | [5 empty] | Changes identified | Not Complete
Health Practitioner Licensure (eLicense) | IP | IP | [5 empty] | Changes identified
Adult Blood Lead Epidemiology and Surveillance (ABLES) | IP | IP | [5 empty] | Changes identified
CT Influenza Surveillance: Now part of CT EDSS | IP | IP | [5 empty] | Changes identified
Tuberculosis Program (formerly TIMS) | NC | NC | [5 empty] | Not able to make changes due to lack of time and staffing
Occupational Injury and Illness Surveillance | IP | IP | [5 empty] | Changes identified
Surveillance Epidemiology and End Results (SEER) Data Management System | IP | IP | [5 empty] | Changes identified
GANTT Chart Data | Status Report as of 7/01/2012
| Database | Date Identified | Days Completed | Days Remaining | Date Terminated | Based on project ending November 30, 2012
| Births | 2012-05-10 | 52 | 152 |  | 2012-11-30
| CIRTS | 2012-05-10 | 52 | 152 |  | Status Reports
| HP Licensure | 2012-05-10 | 52 | 152 |  | 2012-07-01
| ABLES | 2012-05-22 | 40 | 152 |  | 2012-08-30
| CT EDSS | 2012-05-22 | 40 | 152 |  | 2012-10-01
| TB (TIMS) | 2012-05-22 | 1 | 0 | 2012-05-22 | 2012-11-30
| OISS | 2012-05-22 | 40 | 152
| SEER | 2012-05-22 | 40 | 152